## Slide 1: Davar Rezania PhD, CPA, CMA
Leadership and Management of a Diverse Project Team
Estimation and Network Diagram

## Slide 2: Agenda
Estimation
Network diagram

## Slide 3
HR renewal
1. Project documentation
2. Recruitment handbook
3. Performance Management handbook
4. Leadership development handbook
2.1 Job specification guideline
2.2 Selection criteria guideline
2.3 Advertisement guideline
2.4 Selection guideline
2.5 On boarding guideline
3.1 Objective setting guide
3.3 Forced ranking guide
3.4 Reward/punishment guide
4.1 List of desired behaviors
4.2 Assessment methods
4.3 List of potential development training
3.2 Performance evaluation guide
5 Implementation
plan

## Slide 4
Estimating time and cost of deliverables
  The process of forecasting or approximating
  balancing stakeholders’ expectations and the need for control

## Slide 5: Why estimate
Scheduling: determine time and cost
Decide if the project is worth doing
decide cash flow needs
For progress report and control

## Slide 6
Types of Estimates
  Top-down (macro) estimates
  Bottom-up (micro) estimates

## Slide 7: Methods of estimation
Consensus method
Apportion Method
…

## Slide 8: Best practices for estimation
Assume normal conditions, efficient methods, and a normal level of resources
Ask experts to make the estimate
Use more than one person to make estimates (consensus method)
Use consistent units (e.g. for time)
Estimate each work package, don’t aggregate
Reconcile top-down and bottom-up estimates
No allowances for contingencies, but make a risk assessment.

## Slide 9
 |  |  | name | Duration (days) | dependancy
Project documentation |  |  |  |  | 
 | Recruitment handbook |  |  |  | 
 |  | Job specification guideline | A | 3 | I
 |  | Selection criteria guideline | B | 4 | I
 |  | Advertisement guideline | C | 2 | I
 |  | Selection guideline | D | 4 | B
 |  | On boarding guideline | E | 2 | A
 | Compensation handbook |  |  |  | 
 |  | Objective setting guide | F | 2 | I,A
 |  | Forced ranking guide | G | 4 | F
 |  | Reward/punishment guide | H | 7 | F
 | Leadership development handbook |  |  |  | 
 |  | List of desired behaviors | I | 2 | 
 |  | Assessment methods | J | 3 | I
 |  | List of potential development training | K | 2 | I
 | Implement |  |  |  | 
 |  | plan implementation | L | 5 | A-K

## Slide 10: Terminology
Activity: an element that requires time but may not require resources
Merge Activity: has two or more preceding activities on which it depends
Burst Activity: an activity that has more than one activity immediately following it
Parallel Activities: Activities that can occur independently
Path: a sequence of connected, dependent activities
A
B
D
C
E

## Slide 11: Network rules
Networks typically flow from left to right.
An activity cannot begin until all preceding connected activities are complete.
Looping is not allowed.
Conditional statements are not allowed.
Use common start and stop nodes.

## Slide 12
 | ID | 
 | Activity description | 

## Slide 13
 | I | 
 | Desired behaviour | 

## Slide 14
 | I | 
 | Desired behaviour | 
 | A | 
 | Job spec | 
 | B | 
 | selection | 
 | C | 
 | advertise | 
 | F | 
 | Objective setting | 
 | J | 
 | assessment | 
 | K | 
 | training | 

## Slide 15
 | I | 
 | Desired behaviour | 
 | A | 
 | Job spec | 
 | B | 
 | selection | 
 | C | 
 | advertise | 
 | F | 
 | Objective setting | 
 | J | 
 | assessment | 
 | K | 
 | training | 

## Slide 16
 | I | 
 | Desired behaviour | 
 | A | 
 | Job spec | 
 | B | 
 | selection | 
 | C | 
 | advertise | 
 | F | 
 | Objective setting | 
 | J | 
 | assessment | 
 | K | 
 | training | 
 | H | 
 | Reward and punishment | 
 | G | 
 | Forced ranking | 
 | L | 
 | Plan Implement | 
 | E | 
 | On boarding | 
 | D | 
 | Selection | 

## Slide 17
 | I | 
 | Desired behaviour | 
 | A | 
 | Job spec | 
 | B | 
 | selection | 
 | C | 
 | advertise | 
 | F | 
 | Objective setting | 
 | J | 
 | assessment | 
 | K | 
 | training | 
 | H | 
 | Reward and punishment | 
 | G | 
 | Forced ranking | 
 | L | 
 | Plan Implement | 
 | E | 
 | On boarding | 
 | D | 
 | Selection | 

## Slide 18
 | I | 
 | Desired behaviour | 
 | 2 | 
 | A | 
 | Job spec | 
 | 3 | 
 | B | 
 | selection | 
 | 4 | 
 | C | 
 | advertise | 
 | 2 | 
 | F | 
 | Objective setting | 
 | 2 | 
 | J | 
 | assessment | 
 | 3 | 
 | K | 
 | training | 
 | 2 | 
 | H | 
 | Reward and punishment | 
 | 4 | 
 | G | 
 | Forced ranking | 
 | 4 | 
 | L | 
 | Plan Implement | 
 | 5 | 
 | E | 
 | On boarding | 
 | 4 | 
 | D | 
 | Selection | 
 | 2 | 
 | Id | 
 | activity | 
 | duration | 

## Slide 19: Forward Pass
early start (ES)
early finish (EF)
Initial ES = 0
Add activity times along each path (ES + Duration = EF).
Carry the EF to the next activity where it becomes its ES, unless…
The next succeeding activity is a merge activity, in which case the largest EF number of all its immediate predecessor activities is selected.
ES | I | EF
 | activity | 
 | 2 | 

## Slide 20
0 | I | 2
 | Desired behaviour | 
 | 2 | 
2 | A | 5
 | Job spec | 
 | 3 | 
2 | B | 6
 | selection | 
 | 4 | 
2 | C | 4
 | advertise | 
 | 2 | 
5 | F | 7
 | Objective setting | 
 | 2 | 
2 | J | 5
 | assessment | 
 | 3 | 
2 | K | 4
 | training | 
 | 2 | 
 | H | 
 | Reward and punishment | 
 | 4 | 
 | G | 
 | Forced ranking | 
 | 4 | 
 | L | 
 | Plan Implement | 
 | 5 | 
 | E | 
 | On boarding | 
 | 4 | 
 | D | 
 | Selection | 
 | 2 | 

## Slide 21
0 | I | 2
 | Desired behaviour | 
 | 2 | 
2 | A | 5
 | Job spec | 
 | 3 | 
2 | B | 6
 | selection | 
 | 4 | 
2 | C | 4
 | advertise | 
 | 2 | 
5 | F | 7
 | Objective setting | 
 | 2 | 
2 | J | 5
 | assessment | 
 | 3 | 
2 | K | 4
 | training | 
 | 2 | 
 | H | 
 | Reward and punishment | 
 | 4 | 
 | G | 
 | Forced ranking | 
 | 4 | 
 | L | 
 | Plan Implement | 
 | 5 | 
 | E | 
 | On boarding | 
 | 4 | 
 | D | 
 | Selection | 
 | 2 | 
Complete the diagram

## Slide 22
0 | I | 2
 | Desired behaviour | 
 | 2 | 
2 | A | 5
 | Job spec | 
 | 3 | 
2 | B | 6
 | selection | 
 | 4 | 
2 | C | 4
 | advertise | 
 | 2 | 
5 | F | 7
 | Objective setting | 
 | 2 | 
2 | J | 5
 | assessment | 
 | 3 | 
2 | K | 4
 | training | 
 | 2 | 
7 | H | 14
 | Reward and punishment | 
 | 7 | 
7 | G | 11
 | Forced ranking | 
 | 4 | 
14 | L | 19
 | Plan Implement | 
 | 5 | 
5 | E | 9
 | On boarding | 
 | 4 | 
6 | D | 8
 | Selection | 
 | 2 | 

## Slide 23: Backward Pass
starting with the project end activity, compute:
Late finish (LF)=Early finish (EF)
late finish - Duration = late start.
Carry the LS to the next preceding activity: it becomes its LF unless it is a burst activity
burst activity: smallest LS number of all its immediate successor activities is selected.
ES | I | EF
 | activity | 
LS | Duration | LF

## Slide 24
0 | I | 2
 | Desired behaviour | 
 | 2 | 
2 | A | 5
 | Job spec | 
 | 3 | 
2 | B | 6
 | selection | 
 | 4 | 
2 | C | 4
 | advertise | 
 | 2 | 
5 | F | 7
 | Objective setting | 
5 | 2 | 7
2 | J | 5
 | assessment | 
 | 3 | 
2 | K | 4
 | training | 
 | 2 | 
7 | H | 14
 | Reward and punishment | 
7 | 7 | 14
7 | G | 11
 | Forced ranking | 
10 | 4 | 14
14 | L | 19
 | Plan Implement | 
14 | 5 | 19
5 | E | 9
 | On boarding | 
 | 4 | 
6 | D | 8
 | Selection | 
 | 2 | 
ES | I | EF
 | activity | 
LS | D | LF

## Slide 25
0 | I | 2
 | Desired behaviour | 
 | 2 | 
2 | A | 5
 | Job spec | 
 | 3 | 
2 | B | 6
 | selection | 
 | 4 | 
2 | C | 4
 | advertise | 
 | 2 | 
5 | F | 7
 | Objective setting | 
5 | 2 | 7
2 | J | 5
 | assessment | 
 | 3 | 
2 | K | 4
 | training | 
 | 2 | 
7 | H | 14
 | Reward and punishment | 
7 | 7 | 14
7 | G | 11
 | Forced ranking | 
10 | 4 | 14
14 | L | 19
 | Plan Implement | 
14 | 5 | 19
5 | E | 9
 | On boarding | 
 | 4 | 
6 | D | 8
 | Selection | 
 | 2 | 
ES | I | EF
 | activity | 
LS | 2 | LF
Complete the diagram

## Slide 26
0 | I | 2
 | Desired behaviour | 
0 | 2 | 2
2 | A | 5
 | Job spec | 
2 | 3 | 5
2 | B | 6
 | selection | 
8 | 4 | 12
2 | C | 4
 | advertise | 
12 | 2 | 14
5 | F | 7
 | Objective setting | 
5 | 2 | 7
2 | J | 5
 | assessment | 
11 | 3 | 14
2 | K | 4
 | training | 
12 | 2 | 14
7 | H | 14
 | Reward and punishment | 
7 | 7 | 14
7 | G | 11
 | Forced ranking | 
10 | 4 | 14
14 | L | 19
 | Plan Implement | 
14 | 5 | 19
5 | E | 9
 | On boarding | 
10 | 4 | 14
6 | D | 8
 | Selection | 
12 | 2 | 14
ES | I | EF
LF-EF | activity | 
LS | D | LF
Complete the diagram

## Slide 27
Critical path is the longest path through the activity network, the path(s) that has (have) the least slack in common.
Is the shortest planned time in which the project can be completed.